## Input Data
Course Development | Enter data in this column
Duration of course (hours) | 2 | Hours
Difficulty Level to design course | 40 | Enter 30 for average class, 40 for more advanced training classes, or 50 for highly technical training
Multimedia Level | 1.5 | Enter 1 for little or no multimedia, 1.5 for some multimedia, and 2 if the course is composed mostly of multimedia
Experience Level of Designers | 0.8 | Enter 1.2 for new designers, 1 for average skill sets, and 0.8 for designers with advanced skills
Number of Instructors per hour of training | 0.5 | If course is blended learning, then enter percentage of time instructors will be used. For example, if 1/2 the class is asynchronous elearning, then enter 0.5
Learners
Total number of learners to be trained | 20
Class Size | 4
Travel cost | 1200 | Enter average travel cost for a participant
Average pay of learner | 23 | per hour
Misc (in dollars)
Equipment | 350
Outside vendor | 0
Consultant | 0
Video | 600
Other | 160
Results are are given in the "Training Estimates" worksheet
Note: Enter your own data in column B. In addition, you might have to adjust the numbers in column C to fit your own organization
This tool is part of a larger set at:
http://nwlink.com/~donclark/hrd/templates/templates.html
Cost

## Training Estimates
Note that the calculations on this page are based upon the data enter into the "Input Data" spreadsheet
| Percentage of Time | Hours
Needs Assessment | 3% | 2.88
Prepare Project Plan | 2% | 1.92
Conduct Course Content/Learning Analysis | 5% | 4.8
Develop Instructional Media Design Package | 10% | 9.6
Develop Prototype Lesson | 5% | 4.8
Develop Flowcharts | 3% | 2.88
Develop Script/Storyboards | 19% | 18.24
Produce/Acquire Media (Photos, audio, video) | 13% | 12.48
Author Course | 30% | 28.8
Evaluate the Course (In-Process Reviews) | 10% | 9.6
| 100% | 96 | Total Hours to create course
Instructor Prep Time |  | 3 | hours
Labor Cost
Instructional Designer labor cost |  | 2768.64
Instructor labor cost |  | 230.72
Learner's wages |  | 460
Travel costs |  | 24000
|  | 27459.36 | Total
Misc Costs:
Equipment |  | 350
Outside vendor |  | 0
Consultant |  | 0
Video |  | 600
Other |  | 160
|  | 28440.36 | Grand Total
Note: You might have to adjust the percentages to fit your organization, if so, ensure the percentage add up to 100%

## Notes
Produce a video | 2000 | per-finished-minutes (PFM) depending upon concept, locations, talent, special effects, etc.
Produce slides | 25 | per slide
Produce audio tape | 75 | per minute
Student guide | 88 | four to eight hours development time to produce 1/2 to 2 pages
Instructional Designer | 28.84 | based on salary of $60,000 per year
Management or Organization Specialist | 38.46 | based on salary of $80,000 per year
Outside Consultant or Specialist | 85 | per hour
Instructor Preparation: |  | (Dugan Laird, in "Approaches to Training and Development," (1985) Based on U.S. Civil Service estimate):
| 3 | Course is five days or less, then 3 hours of preparation for each hour of training.
| 2.5 | Course is between five and ten days, then 2.5 hours of preparation for each hour of training.
| 2 | Course is over 10 days, then 2 hours of preparation for each hour of training.